## Sheet1
Team mates | Responsibilities | Due date | Completed | Assigned to
Nasreen
Tracie
Jamie
Gadise
Predicting the success of the movie
Deliverable 1: Aug 14th
GitHub | Add comm protocols to README |  |  | Tracie
| Refresh project proposal |  |  | Nasreen
HMTL & Tableau | Begin overview/design proposal |  |  | Jamie / Gadise
Machine Learning | Begin Machine Learning Portion |  |  | Gadise
EDA | Database portion of Segment 1 in ruberic |  |  | Tracie
| 1.Choosing the Data sets |  | x
| 2. Explorating the data in Pandas |  | x
| 3.Performing the transformations on the datasets |  |  | Nasreen
a.Choosing the right columns
b.Changing the column names
c.Removing the null values
d.Dropping the unnecessary columns
4.Merging the datasets based on the common column
5.Loading the data in to SQLlite database
Database | 6.Reading the data from Sqllite,Creating ERD diagram
7.Creating tables,querying the tables to display the data -- atleast 3 tables (Check S3 if needed)
8.Showing the datatypes,Primary key,Foreign key relationships
Deliverable 2: Aug 21st | 1.Reading the dataset
Tableau | 2.Creating two powerful BI dashboards
3.Creating stories for dashboards
4.Include Line,bar,Lollipop,maps charts
5.Custom colors,global filters,Data story
Deliverable 3: Aug 28th | 1.Read the dataset
Machine Learning | 2.Choosing the target and feature variable
3.Compile,Training,Scalin gand modeling the data.
4.Supervised machine learning,tree model,linear model
Deliverable 4: Aug 30th
Final Website | 1.Creating HTML page using CSS,Bootstrap,Java Script
2.Connecting using Flask
Website structure | About us
Dashboard
Machine Learning
Deliverable 5: Sept 1st
Write up | 1.EDA
2.Database - ERD diagram
3.BI - dashboards -Insights
4.Machine Learning - Algorithm,Scaling,Why this model?
5.Website - HTML
Executive Summary | 1.Two sided brief description about the project with images